## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (actual date) | Date finished (actual date)
SI-004 | Seasonal Spending Detection | As a user in China, I want the system to detect and adapt to seasonal spending habits, such as higher expenses during Chinese New Year and Mid-Autumn Festival, so that my budget recommendations are more accurate and relevant to my local context. | Must have | 1 | The system can identify seasonal spending patterns specific to China (e.g., increased spending during Chinese New Year, Mid-Autumn Festival, etc.) The system adjusts budget recommendations to account for seasonal spending spikes Users can view historical seasonal spending trends in a visual format (e.g., charts) The system provides notifications when approaching high-spending seasons Users can manually adjust seasonal spending expectations if needed | 5 days | Ensure the system can accurately detect and differentiate between regular spending and seasonal spikes. The user interface should clearly highlight seasonal adjustments in budget recommendations. | 2025-03-20 | 2025-03-25
SI-005 | Multi-Region Spending Habits Integration | As a user who frequently travels between cities and rural areas with significantly different spending levels, I want the system to dynamically adjust budget recommendations based on my actual living scenarios, so that my budget planning better aligns with the actual spending levels in different regions. | Should have | 2 | The system can detect spending differences between regions (e.g., high consumption in urban areas, medium consumption in suburban areas, and low consumption in rural areas) Users can select their current region (e.g., urban or rural area) to receive customized budget recommendations The system provides differentiated budget adjustments based on regional spending levels (e.g., higher transportation costs in cities, lower living costs in rural areas) Users can manually switch region settings, or the system can automatically switch based on spending locations The system visually displays spending trends and budget comparisons across different regions | 6 days | Ensure the system can accurately identify regional differences and provide reasonable budget recommendations. The interface should be user-friendly, supporting manual or automatic region switching. | 2025-03-26 | 2025-03-31
SI-006 | Online Shopping Alerts | As a user who loves online shopping, I want the system to alert me before e-commerce promotions (e.g., Double 11), and provide budget adjustment recommendations, so that I can plan my spending in advance and avoid overspending. | Could have | 3 | The system sends notifications 1-2 weeks before e-commerce promotions (e.g., Double 11，Double 12 and 618) Notifications include budget adjustment recommendations for upcoming promotions Users can set spending limits for promotions The system tracks spending during promotions and provides real-time feedback Users can customize the timing and content of alerts, or disable alerts | 3 days | Ensure notifications are timely and non-intrusive. The system should support customizable alert settings and provide clear spending trend analysis. | 2025-04-01 | 2025-04-05