## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (actual date) | Date finished (actual date)
SI-001 | Manual Transaction Entry | As a financial management user, I want to manually input transaction details, So that I can record cash-based or non-digital transactions. | Must have | 1 | 1. Users can enter date, amount, category, merchant, and notes for each transaction 2. Support multiple currency formats and decimal precision 3. Auto-save draft entries during input 4. Transaction preview before final submission 5. Edit/delete existing manual entries | 5 days | Input interface should mimic physical receipt format for intuitive data entry | 2025-03-21 | 2025-03-26
SI-002 | CSV File Import | As a digital banking user, I want to import structured CSV transaction files, So that I can automatically sync with bank records. | Must have | 1 | 1. Support standard CSV formats from major banks (e.g., 6-column format) 2. Automatic date format detection and conversion 3. Column mapping interface for non-standard files 4. Batch import handling (up to 10,000 records) 5. Import confirmation summary with success/failure counts | 5 days | Need to handle different encoding formats (UTF-8/ANSI) and CSV delimiters | 2025-03-27 | 2025-04-01
SI-003 | Monthly Budget Recommendations | As a financial management user, I want the system to automatically generate monthly budget recommendations based on my historical spending data, So that I can manage my funds more systematically. | Must have | 1 | The system can analyze at least 3 months of historical spending data to generate budget recommendations Budget recommendations are categorized by expense types (e.g., dining, transportation, entertainment) Users can compare budget recommendations with actual spending Budget recommendations consider seasonal factors (e.g., additional expenses during holiday periods) Users can accept, adjust, or reject the system's recommendations | 5 days | Need to ensure the algorithm correctly identifies user spending patterns, even with limited data. The user interface should display percentage differences between recommendations and actual spending. | 2025-03-20 | 2025-03-25
SI-004 | Personalized Savings Goals | As a user who wants to accumulate funds, I want the system to help me set reasonable savings goals based on my income and spending habits, So that I can achieve my financial objectives more effectively. | Should have | 2 | The system analyzes user income and necessary expenses to calculate potential savings amounts Users can set short-term (1-3 months), medium-term (3-12 months), and long-term (over 1 year) savings goals The system provides savings progress tracking and visualization Users can customize savings goal names, amounts, and deadlines The system provides notifications when users approach or reach savings goals | 6 days | Ensure system-recommended savings goals are realistic and achievable, avoiding overly aggressive targets that might cause users to give up. | 2025-03-26 | 2025-03-31
SI-005 | pending Pattern Recognition | As a user who wants to understand my spending habits, I want the system to identify and display my spending patterns and trends, So that I can better understand my financial behavior. | Must have | 1 | The system can identify regular user expenses (e.g., monthly bills, subscription services) The system can display user spending trends by time period (day/week/month/year) in chart form The system can identify and alert abnormal spending behaviors (significantly higher or lower than average) The system can display proportion analysis of user spending by category Users can select different time periods to view spending pattern analysis | 4 days | Charts should be concise and easy to understand, avoiding excessive technical terminology. Abnormal spending alerts should have clearly defined thresholds to avoid excessive user disruption. | 2025-04-01 | 2025-04-05
SI-006 | Automatic Expense Categorization | As a user who wants to track my spending, I want the system to automatically categorize my transactions into predefined categories (e.g., groceries, rent, entertainment), So that I can easily understand where my money is being spent. | Must have | 1 | The system can automatically categorize at least 80% of transactions correctly based on transaction descriptions Users can view categorized transactions in a summary report Users can manually correct misclassified transactions The system learns from user corrections to improve future categorizations The system supports at least 10 predefined categories (e.g., groceries, rent, entertainment, transportation, etc.) | 7 days | Ensure the AI model is trained on a diverse dataset to handle various transaction descriptions. The system should provide a simple interface for manual corrections. | 2025-04-06 | 2025-04-13
SI-007 | Manual Correction of Misclassified Transactions | As a user who wants accurate expense tracking, I want to be able to manually correct transactions that are misclassified by the AI, So that my spending reports are accurate and reliable. | Must have | 1 | Users can manually change the category of any transaction The system saves user corrections and applies them to future similar transactions Users can view a history of corrected transactions The system provides a quick way to undo corrections The system highlights transactions that have been corrected by the user | 5 days | Ensure the manual correction process is intuitive and does not require multiple steps. The system should provide clear feedback when a correction is made. | 2025-03-20 | 2025-03-25
SI-008 | AI Learning from User Corrections | As a user who frequently corrects misclassified transactions, I want the AI to learn from my corrections, So that future transactions are categorized more accurately. | Should have | 2 | The system tracks user corrections and uses them to retrain the AI model The system provides a notification when the AI model has been updated based on user corrections Users can view the impact of their corrections on future categorizations The system allows users to reset the AI model to its original state if needed The system provides a summary of how many corrections have been made and how they have improved categorization accuracy | 8 days | Ensure the AI model updates do not introduce new errors. The system should provide clear feedback on how user corrections are improving accuracy. | 2025-03-25 | 2025-04-02
SI-009 | Customizable Expense Categories | As a user with unique spending habits, I want to be able to create and customize my own expense categories, So that I can track my spending in a way that makes sense to me. | Could have | 3 | Users can create new expense categories and assign them to transactions Users can rename or delete existing categories The system allows users to merge similar categories Users can set default categories for recurring transactions The system provides a warning if a category is deleted and transactions are affected | 6 days | Ensure the customization process is simple and does not disrupt existing categorizations. The system should provide clear warnings when changes affect existing transactions. | 2025-04-03 | 2025-04-09
SI-010 | Seasonal Spending Pattern Detection | As a user who wants to understand my seasonal spending habits, I want the system to detect and highlight seasonal spending patterns (e.g., higher expenses during holidays), So that I can plan my budget accordingly. | Should have | 2 | The system can detect seasonal spending patterns based on historical data Users can view a summary of seasonal spending trends The system provides recommendations for adjusting budgets during peak spending periods Users can manually mark transactions as seasonal expenses The system provides notifications when seasonal spending patterns are detected | 7 days | Ensure the system can differentiate between regular and seasonal spending patterns. The system should provide clear visualizations of seasonal trends. | 2025-03-26 | 2025-04-02
SI-011 | Seasonal Spending Detection | As a user in China, I want the system to detect and adapt to seasonal spending habits, such as higher expenses during Chinese New Year and Mid-Autumn Festival, so that my budget recommendations are more accurate and relevant to my local context. | Must have | 1 | The system can identify seasonal spending patterns specific to China (e.g., increased spending during Chinese New Year, Mid-Autumn Festival, etc.) The system adjusts budget recommendations to account for seasonal spending spikes Users can view historical seasonal spending trends in a visual format (e.g., charts) The system provides notifications when approaching high-spending seasons Users can manually adjust seasonal spending expectations if needed | 5 days | Ensure the system can accurately detect and differentiate between regular spending and seasonal spikes. The user interface should clearly highlight seasonal adjustments in budget recommendations. | 2025-03-20 | 2025-03-25
SI-012 | Multi-Region Spending Habits Integration | As a user who frequently travels between cities and rural areas with significantly different spending levels, I want the system to dynamically adjust budget recommendations based on my actual living scenarios, so that my budget planning better aligns with the actual spending levels in different regions. | Should have | 2 | The system can detect spending differences between regions (e.g., high consumption in big cities, medium consumption in small cities, and low consumption in rural areas) Users can select their current region (e.g., city or rural area) to receive customized budget recommendations The system provides differentiated budget adjustments based on regional spending levels (e.g., higher transportation costs in cities, lower living costs in rural areas) Users can manually switch region settings, or the system can automatically switch based on spending locations The system visually displays spending trends and budget comparisons across different regions | 6 days | Ensure the system can accurately identify regional differences and provide reasonable budget recommendations. The interface should be user-friendly, supporting manual or automatic region switching. | 2025-03-26 | 2025-03-31
SI-013 | Online Shopping Alerts | As a user who loves online shopping, I want the system to alert me before e-commerce promotions (e.g., Double 11), and provide budget adjustment recommendations, so that I can plan my spending in advance and avoid overspending. | Could have | 3 | The system sends notifications 1-2 weeks before e-commerce promotions (e.g., Double 11，Double 12 and 618) Notifications include budget adjustment recommendations for upcoming promotions Users can set spending limits for promotions The system tracks spending during promotions and provides real-time feedback Users can customize the timing and content of alerts, or disable alerts | 3 days | Ensure notifications are timely and non-intrusive. The system should support customizable alert settings and provide clear spending trend analysis. | 2025-04-01 | 2025-04-05
SI-014 | Intelligent Optimization of Investment Portfolio | As an investor, I hope the platform can display my current asset allocation plan, show the main financial indicators of each asset, visually display the asset allocation ratio, and provide suggestions for asset allocation | must have | 1 | 1. List three different types of assets separately and label them with different colors 2. Display the total value, annualized rate of return, and maximum drawdown of assets below them 3. Draw a bar chart to visually display the asset allocation ratio 4. Intelligent generation of asset allocation opinions, pointing out shortcomings | 8days | It is necessary to establish a connection with third-party financial data interfaces to ensure the real-time update of market data. | 2025-03-17 | 2025-03-24
SI-015 | Historical appreciation data of assets | As a person who wants to resume the investment strategy, I hope to see the changes of my assets in the past period, and also hope to see the values of the yields of several mainstream index funds, treasury bond bonds and bank interest rates in the same period for comparison | must have | 1 | 1. Automatically download data from multiple platforms and generate the value of assets that have changed over time over a period of time. 2. Download the yield of mainstream index funds, treasury bond bond interest rate and central bank interest rate from the public database 3. Based on past investment returns, provide feedback and attribute the characteristics of asset changes in conjunction with portfolio data | 7days | Obtaining authorized data is crucial and requires attention to its legality | 2025-03-20 | 2025-03-26
SI-016 | Transaction record and statement system | As an investor, I hope to see what I have done in the past period of time. What projects have I invested in, how much did I spend, and when did the transaction occur. | could have | 5 | 1. Automatically download data from multiple platforms 2. Classifying data can help users know which type a transaction belongs to 3. Display the transaction time, amount, and corresponding transaction fees 4. When there are a large number of transaction orders, support displaying more transaction orders on the sliding interface | 6days | The transaction fees are often calculated on this platform, so it is necessary to pay attention to the different transaction fee policies of different exchanges | 2025-05-28 | 2025-06-03